## Dashboard
Activity | Status | Start | Finish | DD | Owner | Description | Dependency | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02 | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04
Activty Dashboard | Not Started | 2021-08-01 | 2021-08-02 | 2021-08-02 | Tone | Provides overview of all activities at a glance | None at this time
Schedule 1:1 with Team | Not Started | 2021-07-29 | 2021-07-30 | 2021-07-30 | Tone | Sync with each team member | None at this time
New Meeting Time | In Progress | 2021-08-03 | 2021-08-05 | 2021-08-05 | Tone | Discussion via email | Team
Compile feedback | In Progress | 2021-07-28 | 2021-07-30 | 2021-07-30 | Tone | Feedback from initial session, including notes | None at this time
Update Dashboard with feedback tasks | Not Started | 2021-08-02 | 2021-08-02 | 2021-08-02 | Tone | Add all tasks identified in notes and add to dashboard | None at this time
Schedule new Meeting time | Not Started | 2021-08-03 | 2021-08-03 | 2021-08-03 | Tone | Schedule team meeting series | Team input
Dev Env Review | Not Started |  |  |  | Tone, Seth
Hosting Solution Review |  |  |  |  | Seth, Tone, Vaughn
Security Review |  |  |  |  | Team
DB Tables Defined |  |  |  |  | Vaughn, Kevin | TBD- How many tables are needed, arch defined? Kevin - offshore development costs
SP & Trigger Development |  |  |  |  | Vaughn, Kevin | SP is ? Define this activity
User Privileges | Not Started |  |  |  |  | Needs to be defined
Catalog Website Development | Not Started |  |  |  | Andre, Kalil | tentative 7/1 - are there requirements and UI
Design Doc | TBD |  |  |  | TBD | Design Doc - highlevel user stories, sequence diagram, logical diagram | Arch, devs, prod owners
Env - Server Eval | In Progress? | TBD | TBD | TBD | Seth | Assigned 6/12 - meeting notes - may be complete
DB Creation | In progress? | TBD |  |  |  | Assigned back on 6/5
MVP Scope | [5 empty] | What features and functionality will be in the MVP

## Open Issues
Statu | Question | Asked | Answered | Result | Notes
Open | Name of the project? | 2021-06-28
Open | Meeting Cadence | 2021-06-28
Open | Current Tools? | 2021-06-28
Open | REPO? (GIT/Hybrid??) | 2021-06-28
Open | Proudct Asset Status? | 2021-06-28
Open | Airtable - Is the team active on this platform | 2021-06-28 |  |  | https://airtable.com/tblUl16wFPC8webXg/viwG5gQ1BTSHKhNmY?blocks=bip90al4RsVlcru8j
Open | Is there a mockup or MVP? | 2021-06-28 |  |  | meeting on 6/12 to discuss mocking with Andre - Meeting results?
Open | Hosting |  |  |  | Jared, Andre prefer Digital Ocean - Is this still an open issue
Open | DBO Document Creator | 2021-06-28 |  |  | this doesnt sound like the product, however I can see this as an abstract product,,would compete with InDesign.
Open | App Platform (PHP, Java?)
Open | Architecture and User Stories |  |  |  | a meeting on 5/29 identified modules of the application - where are the user stories for each module and the app architecture?

## App-Features
Features
Features | User Stories | Design Doc | MVP Defined | Estimate | Resources | Note
Database | [5 empty] | define by table an correlate to feature
Greeting Personalization Website | [5 empty] | This sounds big and would require IAM, Personalization and standard portal features along with application integration
Order and Print Management
Document Mangement |  | x |  |  |  | Section->Content Management System
User Management | [5 empty] | Define User Management
Vendor Poral | [5 empty] | similar requirement to Personalization site
Report Portal | [5 empty] | Define reporting
Invoice & Billing Portal | [5 empty] | simiilar to personalization with BI
Support portal | [5 empty] | similar to site with case management, search, and documentation

## Links
Asset | URL | Owner | Description

## Team Info
Role | Name | Email | Tel | Comm. Pref. | Availability | Notes
Product Owner | Vaughn Jeffers | Vbjeffers@outlook.com | 8154034898 | TBD | m-f after 5pm cst
Product Owner/QA | Mathew Buisson | mbuisson@buissonfamily.com | TBD | TBD | Sat 0700-1000 | Product Owner & Product QA/Review
Developer | Seth Gravvee | g.murdoch@gravidee.us | TBD | TBD |  | App & DB Developer
Developer | Jared Harrison | jared@elementalbot.com | TBD | TBD |  | App & DB Developer
Developer | Andre Todman | AndreTodman@mac.com | TBD | TBD |  | App Developer
Developer | Kalil Langston | keolangston@gmail.com | TBD | TBD |  | Developer
Business Lead | Kevin Langston | kevin.langston@dbotechnologies.com | TBD | TBD |  | Business lead, stakeholder, incubator
PM | Tony Heard | TBD | TBD | TBD |  | PM & Ops

## Env
Dev Environment |  | Stage ? | Prod?
Database Server | Application and File Server
OS: Windows Server 2019 | OS: Windows Server 2019
RAM: 64 GIG | RAM: 64 GIG
Processor: 8 core | Processor: 8 core
HD: Raid 5 8TB (SSD) | HD: Raid 5 8TB (SSD)
Database: Microsoft SQL Server 2019

## Hosting
Hosting information
Site 1 | Site 2