## DataList
Flow State | Points
Grooming | 1
Defined | 2
In-Progress | 3
Completed | 4
Accepted | 5

## Presentation
Story Number | Owner | Name | Project | Flow State | Points | Estimate | Description | Notes | Dependency | Version | Acceptance Criteria
USPTT00001 | Vaughn Jeffers | Login | Card with Gifts | Defined | 1 | 8 | Retailers are assigned IDs. When a retailer login they will access a giftwithcard landing page designed with their logo and selected greeting cards. This will be based on retailer configurations. |  | Landing Page Design Retailer Configuration Defined logos Defined Retailer ID | 1 | When a retailer login the landing page should display a list of greeting cards slected for that retailer, retailer logo, retailer name and retailerid.

## Business Logic
Story Number | Owner | Name | Project | Flow State | Points | Estimate | Description | Notes | Dependency | version | Acceptance Criteria
USPTT00001 | Vaughn Jeffers | Order Creation | Card with Gifts | Grooming | 2 | 16 | When a user puches out to the GiftwithCard site. A token will be passed from the retailer on the URL. The url will also include the retailerid, locationid, retailer orderid, user phone and user address. The user will select and personalize a greeting card. GiftwithCard will store all the greeting card information along with the personalization. GiftwithCard will pass the information back to the retailer site when the user select "Add to Card". The retailer will store the card information as a line item. |  | Landing Page Design Retailer Configuration Defined logos Defined Retailer ID | 1 | When a retailer login the landing page should display a list of greeting cards slected for that retailer, retailer logo, retailer name and retailerid.

## Data
Story Number | Owner | Name | Project | Flow State | Points | Estimate | Description | Notes | Dependency | version | Acceptance Criteria
USPTT00001 | Vaughn Jeffers | Card Publisher | Card with Gifts | Grooming | 4 | 32 | When a publisher uploads a new card to the Gift with Card site it must include 4 separate pages. Those pages are front, back, inside left, inside right. It will also include a text area to list the virbage witten on each page. |  | Publisher login PublisherID Publisher Configuration Publisher contact information Publisher logo/s | 1 | Successful upload of a greeting card that includes four pages, card virbage, card id, publisher id and approve for production option.